## Cover Page
Meal-Prep SPRINT PLAN
Prepared By:Yalan Luo
LIST TEAM MEMBER FULL NAMES WITH STUDENT ID
Mathieu Boileau (40257130)
Christopher Dunn (40285514)
Yalan Luo (40275103)
Muhammad Mobin Syed (40299024)
Ali Kotb (40217082)

## Product Backlog
Story ID# | Pre-Requisite | User title | Story Point | user story | Associated Tasks | Story points associated to a US | Priority | Risk (High, Medium, Low) | Responsible | Due date
US.1 | None | Implement Frontend UI for Home and User Authentication Pages | 5 | As a user, I want the option to log in or register so that I can access the application based on my account status. | Create home page / Log in / account page / register page | 1 | HIGH | HIGH : As a core and critical component of the website, any defects in the login functionality may prevent users from accessing their accounts or result in potential data access risks. | -Mathieu -Christopher - | January 31st
US.2 | none | Profile Management | 5 | as a user I want to be able to change my diet preferences, profile informations, and alergies | Create list of diet preferences and implement in page , create a alergies and page for it aswell | 2 | MEDIUM | LOW ：It determines whether users can access the website’s core functionality based on their account information after login. | -Muhammad | February 2nd
US.3 | US.1 & US.2 | Customizing UI | 4 | As a user, I expect the website's pages and webpage themes to be relevant. | Improve log in pages + all associated Pages + make logo.The button changes color when the mouse hovers over it, providing instant feedback. | 3 | LOW | LOW：It determines whether users can recognize and use the various features of the website. Unclear UI design leads to a degraded user experience. | Yalan , Ali | February 5th
US.4 | US.1 & US.2 | Implement Backend Services for User Management and Data Handling | 7 | As the system, I need to provide a backend for the website so that the frontend can interact with data, manage users, and deliver full functionality. | Create database which includes diet preferences, allergies, username and password. Create a function that receives data from registration and stores it in the database. Include error checking in the registration to ensure unique usernames | 4 | HIGH | HIGH：It determines whether input data across the website can be properly linked and stored. Incorrect associations may cause system failures and lead to leakage of other users’ information. | -Mathieu -Christopher - Muhammed | February 4th
[5 empty] | Total: | 10
Story ID# | Pre-Requisite | User title | Story Point | user story | Associated Tasks | Story points associated to a US | Priority | Risk (High, Medium, Low) | Responsible | Due date
US .5 | US.1, US.4, | Create edit and delete recipes | 5 | As a user, I want the option to create and manage my own recipes | frontend: create a front end form that collects all information(steps, ingredients, preperation, dietary tags, difficulty, duration, cuisines, equipment) / create button that lets the user modify recipe. attributes / create button to delete recipes Backend: create class called recipe that can receive data from the form and store the data in the txt file. create function that receives button input that lets the user modify recipes. create a function that deletes recipe object from array | 1 | HIGH : | HIGH : This needs to be done right away, every user story in this iteration will depend on this user story. Users may accidentally delete a recipe, causing permanent data loss | MOE CHRIS | 2026-02-20
US.6 | US.5 | Search recipes | 5 | As a user, i want to be able to search recipes that I have already created | Create Search recipes page / Create a backend to handle search requests/ Connect the frontend to the backend ./Design and implement the search bar on the frontend. | 3 | MEDIUM | HIGH : It determines wheter users can search recipes or not.Search results may include irrelevant or duplicated recipes | MOE Mathieu | 2026-02-27
US.7 | US.5 | filter recipes | 4 | As the user, I need to have the option to filter recipes by , Time, difficulty, cost, dietary tag, etc. | Implement frontend logic to send selected filters to the backend | 3 | MEDIUM | MEDIUM：Search results may include irrelevant or duplicated recipes. | ALI YALAN | 2026-02-27
US.8 | US.1 | Add CSS to registration page | 7 | As the user, id would like the registration to be more user friendly with better style | update the CSS file for the registration page. | 4 | LOW | LOW：It determines whether users can recognize and use the various features of the website. Unclear UI design leads to a degraded user experience. | CHRIS | 2026-02-20
US.9 | US.5 | Create a page to view recipes | 8 | As a user, after I am authenticated and loaded into the home page, i would like to see some of the recipes i have already created | Create frontend page that the user can interact with to view recipes / dynamically display global and personal recipes | 6 | High | HIGH: as soon as the user logs in, this page is what they see, the user should be able to see recipes without explicitly searching, if not well implemented, will hurt customer experience | Mathieu MOE | 2026-02-27

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s):
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
US-1 | UT-1.1 | <create account page> | Developed the user account page | 2 | Completed | See github
| UT-1.2 | <Create home page> | Developed the bear bones of the home page
| UT-1.3 | <Create login page> | Developed the login page that includes the form of the username and password |  | Completed
| UT-1.4 | <create register page> | Registration page will include username, password | 3 | Completed
US-2 | UT-2.1 | <crerate allergy and preferences> | implement UI to allergies and prefences on registration page
US-3 | UT-3.1 | <Customize log in page/home page/register page> | Design the logo, change backgroung size and position. Set header color butter color, hover color and background color. | 4 | Completed
| UT-3.2 | <Customize account page> | Implement UI for account page matchinchg colours with the predetermined format | 4 | Completed
| UT-3.3 | <Customize home page> | Implement UI for home page matchinchg colours with the predetermined format
US-4 | UT-4.1 | Create database | this database should store username, password, diet and allergies. will also assign userID | 5 | Completed
| UT-4.2 | Create a function that receives data from registration and stores it in the database. | Once the user presses register, data should be sent to the database to be stored | 3 | Completed
| UT-4.3 | <add authentication during login process> | Implement a login function that receives the username, checks if the username is stored in the database, if yes check password and redirect to home page if successful, or tell user the information is incorrect | 5 | Completed
| UT-4.4 | <Ensure unique and valid credentials during registration> | during registration, the function should verify if a username already exists, if yes the user should be notified to change it, if no, continue to successful registration process. minimum characters for username and password should be 6 | 5 | Completed
|  |  | Total Hours planned | 31
|  |  | Sprint 1 velocity | 45 |  | Points per week
Note on E7: ECE: Should be less than 5

## Product backlog 2 sample (hidden)
| User Story Title/Task Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Assignmed Members
#1 | Story 1: A user should be able to register account | - create a homepage interface - design and implement a search bar | 5 | 2023-10-20 | High | medium | Steven, Daniel
#1 | Story 1 A user should be able to login account |  | 5 | 2023-10-21 | High | high | Ceyhun, Alex, Ben
#2 | A user can clearly know information from the page and easy to use. | Design the logo, Color change on design hover, Added background | 4 | 2026-02-10 | High | low | yalan
#2 | Story 3:A user can set profit information | - add a "My properties" button in the homepage that lead to property listing view page - develop an interface for brokers to view their property listing | 4 | 2023-10-23 | High | medium | Steven, Daniel, Ben
#3 |  | - in the My Properties page, add a button and forms for adding new properties and deleting existing properties - implement backend logic for adding and deleting properties in the database | 4 | 2023-10-24 | High | high | Ceyhun, Alex, Ben
#4 | Story 4: | - create an interface for administrators to add and remove broker profiles in the system - develop forms to collect broker profile information - implement backend logic to create and remove broker profiles in the database | 4 | 2023-10-25 | High | high | Steven, Ceyhun
|  | Total | 26

## Sprint 2
Sprint 2 Backlog
Sprint 2 Goal(s):
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
US.5 | UT 5.1 | Develop recipe creation form | Develop a dedicated page containing a form that allows users to input recipe information, including title, ingredients, instructions, cost, preparation time, and other relevant attributes. | 2 | Completed
| UT 5.2 | Develop recipe edit form | Devolped the recipe editing form, should load selected recipe information into the form and user can make changes | 2 | Completed
| UT 5.3 | Backend for creation form | once form is submitted, the data should get saved in the database | 2 | Completed
| UT 5.4 | Backend for edit form | once the user clicks edit on the recipe, all the information should be loaded into the form, user can make changes here, once saved it should change the existing recipe details | 2 | Completed
| UT 5.5 | design delete button | design delete button which will be located on each recipe card | 2 | Completed
| UT 5.6 | design delete button | Implement backend API endpoint to support recipe deletion | 2 | Completed
| UT 5.7 | design edit button | edit button should bring the user to the edit page. it should be located on the recipe card
US.6 | UT 6.1 | design search input bar. | design search button on the view recipe page | 0.5. | Completed
| UT 6.2 | back end search button | Implement backend API endpoint to support meal search functionality | 2 | Completed
US.7 | UT 7.1 | design filter form | implement a form on the view recipe page that allows users to find recipes by filtering through recipe attributes such as cost, time |  | Completed
| UT 7.2 | Back end filter form | The form should capture user input, send filter parameters to the backend API, and dynamically display matching recipes without reloading the page. |  | Completed
US.8 | UT 8.1 | add customization to the registration page | update the CSS file for the registration page. | 1 | Completed
US.9 | UT 9.1 | load recipes to the view recipe page | Dynamically load recipes from database into view recipe page | 1.5 | Completed
| UT 9.2 | create view recipe page | create view recipe page that enables the user to view all recipes. this page should also contain the edit, delete and filter function | 1.5 | Completed
Note on E7: ECE: Should be less than 5